## Sheet1
Aitea - QFPay Payment Gateway Integration Project Timeline
# | Task | Task M.D. | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14 | DAY 15 | DAY 16
|  |  | 06/23/2020 | 06/24/2020 | 06/25/2020 | 06/26/2020 | 06/29/2020 | 06/30/2020 | 2020-01-07 | 2020-02-07 | 2020-03-07 | 2020-06-07 | 2020-07-07
1 | Initial Development | 2.5 | bar: DAY 1 to DAY 3
2 | Testing with QFPay Team | 2.5 | bar: DAY 3 to DAY 5
3 | Integration with Merlin Team *** Depends on when they will provide doc for request params | 3 | bar: DAY 6 to DAY 8
4 | UAT | 2 | bar: DAY 9 to DAY 10
5 | Release Deployment | 1 | bar: DAY 11
| Total | 11